## Risk register
SEVEN-G
P12 · Risk matrix and register
Fernando García · SEACHAD · Content CC BY 4.0 · Code MIT · Version 0.1 (working draft) · Generated on 2026-09-23
Replace or delete the example row; add one row per item. Columns with a dropdown only accept the values in their list.
No. | Risk (cause, event and consequence) | Category | Reference typical risk | System or phase | Risk owner | Date added | Inh. L (1–5) | Inh. I (1–5) | Dominant axis | Inherent level | Existing and effective controls | Res. L (1–5) | Res. I (1–5) | Residual level | Trend | Response | Planned controls (P13) | Accepted by | Acceptance date | Status | Next review
R01 | Through a prompt injection in a customer's message, the assistant reveals order data belonging to another customer, causing harm to the affected person and a possible breach of the GDPR. | GEN | GEN catalogue of document 33 | Enquiries assistant · phases 5–6 | AI Technical Owner | 2026-11-20 | 4 | 4 | People and rights |  | Session isolation per customer; output filter for personal data; injection testing with 0 leaks | 2 | 4 |  | Falling | Mitigate | Output monitoring with alerting (P25) | AI Sponsor, with clearance from the AI Risk Owner | 2027-01-15 | Accepted | R6 in the second quarter of 2027