# Pre-session note and note of conclusions for the board session

Prepares the board session on AI with a two-page pre-session note and a timed agenda, and records what was concluded, decided and assigned within the following two working days.

| Document | Template P68 · Pre-session note and note of conclusions for the board session |
| --- | --- |
| Version | 0.1 (working draft) |
| Date | 19-09-2026 |
| Author | Fernando García Varela |
| Status | Draft for review. |

Legal notice and disclaimer. SEVEN-G is a reference methodological framework provided "as is" and for information purposes only. It does not constitute legal, regulatory, financial or professional advice, nor does it guarantee compliance with any law or standard. References to general regulation (such as the EU AI Act, the GDPR, DORA or NIS2), to technical standards and to regulation specific to each sector or jurisdiction may be incomplete, may not apply to a particular case or may become out of date as a result of regulatory changes, interpretations or supervisory positions after their consultation date. Each organisation that uses SEVEN-G is solely responsible for identifying the regulation that applies to it, verifying that it is current and certifying its own regulatory compliance, with the appropriate qualified advice. This methodology is a generic, free aid shared with the community so that nobody has to start from scratch; each person or organisation can and should adapt it to its own use. It must not be inferred that its legally sensitive parts have been reviewed by legal counsel: those reviews, for each company or sector, are the ultimate responsibility of the company, consultant or organisation that uses it. Although every effort is made to keep it up to date, some regulation may have changed without being reflected here. To the fullest extent permitted by law, the author accepts no responsibility whatsoever for the effects of its application in any organisation or for its full applicability. The methodology does not grant certification of any kind. The author accepts no liability for any use made of this content or for any decisions taken on the basis of it. The data, figures, companies and cases in the examples are fictitious or illustrative.

Why it matters. A board session on AI without a pre-session note turns into a presentation; a session without a note of conclusions depends on the memory of those present. The pre-session note tells directors what they will be asked and what decision will be requested of them; the note of conclusions records the priority spheres, the position on people, what was decided and what was assigned, with an owner and a date, and feeds the register of decisions and recommendations (P69). Without them, the session ends with "we will look into it".

# 1. Instructions for use

| Aspect | Guidance |
| --- | --- |
| When it is used | At the first working session with the board on AI (60-minute script in 61 §8, before C1 or as the opening of C2) and, with the variant in section 5.2, at C4 oversight sessions (61 §8.5). |
| Who completes it | The presenter (senior management, chair of the AI Committee or AI Office) drafts the pre-session note and the note of conclusions; the board secretariat circulates it and records what was decided. |
| Who verifies it | The chair of the board or of the board committee reviews the pre-session note before it is circulated; the director or adviser with AI experience may review it if commissioned to do so (91 §4.5). |
| Who decides or approves | The board or its board committee decides at the session. The note of conclusions does not replace the minutes (P39), which the body approves in accordance with its regulations. |
| Stage or point | Before C1 or opening of C2 (first session); C4 (oversight). Circulation one week before; conclusions within 2 working days; recording within 5 working days. |
| Tool | T16 · Portfolio sphere map and T17 · Board AI dashboard as session material; T18 · Board recommendations register for what is decided and assigned. |
| Reference document | Document 61 (§4 response formats, §6 questions per sphere, §8 script); document 60 (pack); document 62 (register). |
| Lite versus Enterprise | The same in both. At Lite the pre-session note may be one page. |

Completion rules:

• The pre-session note is at most two pages long and ends with the decision that will be requested at the end of the session.

• Every question from the board ends up in the register: if it is not answered at the session, it becomes a recommendation or assignment with an owner and a date (61 §2, principle 6).

• Every decision is expressed in one of the four formats: "Yes", "Yes, with one condition: …", "Not yet, because … is missing" or "No, because …". "It depends" is not recorded.

• Business language: the table in 61 §3.2 applies; no untranslated technical jargon and no comparison with the market without a source.

• Examples from the company itself are preferable; if there are none, fictitious examples marked as such are used.

# 2. Identification

| Field | Content | Guidance |
| --- | --- | --- |
| Type of session |  | First session (61 §8) · C4 oversight (61 §8.5) · Other (specify). |
| Body |  | Full board · Board committee (which one). |
| Date and duration |  | DD-MM-AAAA; 60 minutes as reference. |
| Presenter |  | Name, position and SEVEN-G role. |
| Board secretariat |  | Responsible for circulation and recording. |
| Director or adviser with AI experience |  | If any; current declaration of interests (61 §10.3). |
| Previous reference session |  | Date and reference to the minutes, if any. |
| Associated pack |  | P67 in a C4 session. |
| Note version |  |  |

# 3. Preparation

| When | What (61 §8.2) | Who | Planned date | Done (Yes · No) |
| --- | --- | --- | --- | --- |
| Two or three weeks before | Short interviews with the chair, the chair of the board committee and senior business, technology and risk management. Preliminary inventory of AI systems. | The presenter, with the AI Office if there is one |  |  |
| Two weeks before | One example per ambition level in spheres 01 to 04, ideally from the company itself. | The presenter |  |  |
| One week before | Circulation of the pre-session note (section 4). | Board secretariat |  |  |
| The day before | Timed rehearsal: each block fits its time or is cut. | The presenter |  |  |

# 4. Pre-session note (two pages at most)

| Field | Content | Guidance |
| --- | --- | --- |
| Session objective |  | One or two sentences. Example: "Position the company on the impact map and decide whether to commission the diagnosis and the governance structure within ninety days". |
| Why it is a board matter |  | Risk, opportunity, accountability and competitive advantage, in three or four lines. |
| The nine spheres |  | Where value is created (01–04), enablers (05–07), boundaries (08) and meta-sphere (09), in a short table or with the sphere graphic component. |
| The three ambition levels |  | Optimise, Augment and Transform: three types of bet with different cost, risk, time frame and organisational resistance, not a ladder. |
| Preliminary situation of the company |  | What is known today: preliminary inventory, known use cases by sphere and level. What is not known is stated as no data. |
| Reference questions |  | Those for the spheres to be covered (61 §6), in particular the one for each block of the script. |
| What the board will be asked |  | The final decision, worded so that it can be approved or rejected. Example: "Do we commission the diagnosis and the governance structure within ninety days?". |
| What directors are asked to do before the session |  | For example, note the two or three spheres that concern them most. |
| Supporting material |  | Sphere map (T16), dashboard (T17) or pack (P67); annexes are not presented in session. |

(illustrative example) Preliminary situation: "14 AI systems have been identified, 9 of them from suppliers; none has been classified with legal judgement. All known use cases are Optimise in spheres 01 and 04. There is no data on validated value."

# 5. Agenda and script

## 5.1 First session (61 §8.3)

| Block | Minutes | Objective | Question for the board | Material | Owner | Outcome noted at the session |
| --- | --- | --- | --- | --- | --- | --- |
| 01 · Strategic framing | 0–10 | Position AI as a business issue and present the impact map. | Which two or three spheres concern you most today? | Sphere component; ambition levels (00 §4.1) |  |  |
| 02 · Spheres where value is created | 10–22 | See where the company's AI is today and where it could be. | Are we using AI to protect the current product or to build the next one? | Map of the portfolio by sphere and level |  |  |
| 03 · Enabler spheres | 22–32 | Diagnose real capability in data, knowledge and decision. | What does AI decide alone, what requires human validation and what is never delegated? | Interview findings; inventory with autonomy A0–A3 if known |  |  |
| 04 · Regulation, ethics and accountability | 32–42 | Find out whether the company governs proactively or reactively. | Do we govern proactively or do we wait for the regulator to force us? | Summary regulatory mapping with consultation date (document 34) |  |  |
| 05 · Position on people | 42–50 | Obtain an explicit position from the board. | Will AI replace, augment or reorganise people's work? | Roles of recipients, subjects and promoters |  |  |
| 06 · AI governance and first 90 days | 50–60 | Close with a decision: mandate, owner and report-back date. | Do we commission the diagnosis and the governance structure within ninety days? | 90-day plan (01 §5.3; document 90) |  |  |

## 5.2 Variant for oversight sessions (61 §8.5)

| Minutes | Content | Supporting document | Owner | Outcome noted at the session |
| --- | --- | --- | --- | --- |
| 0–5 | Main message using the response format; changes since the previous session. | P67 §4 (60 §4.2) |  |  |
| 5–20 | Decisions requested, one by one. | Decision sheets (P67 §5) |  |  |
| 20–35 | Three use cases in detail, five minutes each (61 §5.3). | P67 §10 |  |  |
| 35–45 | Risks, incidents and nonconformities; programme traffic light. | P67 §6 and §9 |  |  |
| 45–55 | Overdue recommendations and discrepancies. | P69; T18 |  |  |
| 55–60 | Summary of decisions and assignments, with owner and date. | Section 7 |  |  |

First item on the agenda of every subsequent session: status of what was decided at the previous session (61 §8.4).

# 6. Note of conclusions (within 2 working days)

| Field | Content | Guidance |
| --- | --- | --- |
| Priority spheres |  | Those indicated by the board in block 01, with the reason. |
| Reading of the portfolio |  | Where the portfolio stands today and whether there is any Transform bet (block 02). |
| Enabling gaps recognised |  | Data, knowledge and decision rules (block 03). |
| Regulatory situation |  | Whether there is an inventory with regulatory classification and who is accountable for it (block 04). |
| Position on people |  | Replace · Augment · Reorganise, even if provisional; or assignment of a proposal for C2 with a date. |
| Decision adopted |  | Using the response format and the proposed DEC code. Executive owner, body that receives the result and date of the report-back session. |
| Questions not answered at the session |  | Each one becomes a recommendation or assignment (section 7). |
| Next session |  | Date and first item on the agenda. |
| Limitations of the session |  | Topics not covered for lack of time or information, and when they will be brought back. |

(illustrative example) Decision adopted: "Yes, with one condition: that the diagnosis includes supplier systems. General management is commissioned to carry out the diagnosis and the governance structure within ninety days; the AI Office will report to the board committee on 15-01-2027. DEC-2026-003."

# 7. Decisions and assignments for the register (within 5 working days)

They are transferred to P69 and T18 with a definitive code.

| # | Proposed code | Type | Text (verifiable) | Owner | Committed date | Body | Recorded in P69 (Yes · No) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 (illustrative example) | DEC-2026-003 | Approve | Commission the AI diagnosis and governance structure within ninety days. | General management | 15-01-2027 | Full board | Yes |
| 2 (illustrative example) | REC-2026-004 | Assignment | Present a proposed position on the effect of AI on employment for the C2 session. | People management | 30-03-2027 | Full board | Yes |

Types: DEC (Approve · Authorise with limits · Accept a risk · Take note) and REC (Recommendation · Assignment), in accordance with 62 §3 and §10.

# 8. Subsequent follow-up

| Time limit (61 §8.4) | Action | Owner | Date | Done (Yes · No) |
| --- | --- | --- | --- | --- |
| 2 working days | Circulation of the note of conclusions. | The presenter |  |  |
| 5 working days | Recording of decisions and assignments with code, owner and date (P69). | Board secretariat |  |  |
| 10 working days after recording | Acceptance of each assignment by its recipient (62 §8, step 3). | Recipients |  |  |
| Next session | First item on the agenda: status of what was decided. | Chair of the AI Committee |  |  |

# 9. Quality criteria

| # | Check | Status (Met · Not met · Not applicable · Pending) |
| --- | --- | --- |
| 1 | The pre-session note fits on two pages and ends with the decision that will be requested. |  |
| 2 | Each block of the script has an owner and fits its time. |  |
| 3 | The session ends with at least one recorded decision with an owner and a date, or with an express record that there was no decision. |  |
| 4 | All decisions use one of the four response formats; no condition affects critical controls. |  |
| 5 | Unanswered questions have been turned into recommendations or assignments. |  |
| 6 | The note of conclusions was circulated within 2 working days and recording was done within 5. |  |
| 7 | The record in the minutes serves as evidence for question D1.02 of document 11 and, in C4, for D1.09. |  |

# 10. Approval and verification

| Function | SEVEN-G role | Name and position | Date | Signature or reference |
| --- | --- | --- | --- | --- |
| Drafts the pre-session note and the note of conclusions | Presenter (senior management, chair of the AI Committee or AI Office) |  |  |  |
| Reviews the pre-session note | Chair of the board or of the board committee |  |  |  |
| Reviews (if commissioned) | Director or adviser with AI experience |  |  |  |
| Circulates and records | Board secretariat |  |  |  |

Segregation of duties: the director or adviser with AI experience may review the note but does not prepare it (61 §10.2); the note of conclusions is drafted by the presenter and the minutes are approved by the body.

# 11. Version control

Completed document

| Version | Date | Author | Changes |
| --- | --- | --- | --- |

Template

| Version | Date | Changes |
| --- | --- | --- |
| 0.1 | 19-09-2026 | First version. Extracts from document 61 the preparation, the two-page pre-session note, the 60-minute script and its oversight variant as an agenda, the note of conclusions and the transfer of decisions and assignments to the register (P69). |